## 12w
Project BEGONIA |  | 12w
Master Development Schedule, 03/19/2017-03/25/2017
SUN, 03/19/2017 | OFF | 12w
12w1d
MON, 03/20/2017 | Mod work of Setings begins
| Adding more AOSP-like look, forcing list format as default | 12w
12w2d | Icon set TBD
TUE, 03/21/2017 | Settings Mod Work
Conversion and importation of icon sources
12w3d | Create a list of features that can be overhauled or removed | 12w
WED, 03/22/2017 | First Modded Settings Release
Internal Release with 1b, public release with 3b if basics work
12w4d | Complete the overhaul/removal list and prepare AptOS branding
12w
THU, 03/23/2017 | Bugfixes and begin overhaul of Settings
Complete Removals first, and then begin on overhauls if time allows
12w5d | Scrap all unnecesary TouchWiz drawables to conserve space
FRI, 03/24/2017 | OFF | 12w
12w6d
SAT, 03/25/2017 | Second Modded Settings Release
| Internal Release with 1b, public release with 3b if basics work | 12w
12w7d | Complete overhauls and begin work on release bootanimation (tp)
RELEASE 3: FINAL
Copyright © 2017 CoreTech Systems, AptLogic. Not to be redistibuted.