## 13w
Project BEGONIA |  | 13w
Master Development Schedule, 03/26/2017-04/01/2017
SUN, 03/26/2017 | OFF | 13w
13w1d
MON, 03/27/2017 | Continue Settings work
| Work on major bugfixes: | 13w
13w2d | Data, USB Storage, and Battery
TUE, 03/28/2017 | Work on minor bugfixes:
Volume
13w3d | Begin work on release bootanimation + testing | 13w
WED, 03/29/2017 | Release day
1b internal, 3b public if everything works
13w4d | Continue bootanimation work
13w
THU, 03/30/2017 | Update day
Update any necessary Google Apps + Release
13w5d | 1b internal, 3b public if everything works
FRI, 03/31/2017 | OFF | 13w
13w6d
SAT, 04/01/2017 | OFF
13w
13w7d | Off due to pre-scheduled event, bootanimation work if time provides
RELEASE 2: PRE-FINAL
Copyright © 2017 CoreTech Systems, AptLogic. Not to be redistibuted.